## Tabelle1
| (P) Probability (estimate) | (S) Severity | (D) Detection (indications to operator, maintainer) | Risk level P*S (+D) | Next higher level effect | Dormancy or latency period
App will not be finished in January | 3 | 4 | 1 | 13 | no higher level effect | will be detected by prof on 14th January
Functional requirements are not met | 3 | 3 | 2 | 11 | this effects that the app will not be finished because these are all conditions which have to work in order to be finished | have been detected by the maintainer (me) now
Non functional requirements (easy to use, …) aren't met | 2 | 1 | 4 | 6 |  | may be detected in some years
SignUp not working (FR) | 1 | 3 | 2 | 5 |  | will be detected when testing (auto detection by maintenance computer)
App is not for everyone | 2 | 2 | 5 | 9